## Worksheet
Measure | Items | Measure name | Indicative Implementation Date | Definitive Implementation Date | TA needs notified | Progress reported | Donor / Agency | TA Description | Tags
1.2 | 1.2.1 (a), 1.2.1 (b), 1.2.1 (c), 1.2.2, 1.2.3 | Information available through internet | 31 December 2020 | 22 August 2023 | Yes | No |  | • Technical assistance and capacity building for establishment, operationalization and sustainability of Trade Facilitation Portal; • Training for HR; • Software and ICT infrastructure to maintain TFP and align with international best practices; • Awareness raising for the private sector on the use of the portal. | Information and communication technologies (ICT), Infrastructure and equipment, Human resources and training, Awareness-raising
1.3 | 1.3.1, 1.3.2, 1.3.3, 1.3.4 | Enquiry points | 31 December 2021 | 22 August 2023 | Yes | No |  | • Legal support on designing, drafting of legislative changes and necessary regulations, SoP, etc.; • Staff capacity building on operating and maintaining enquiry points; • Technical assistance, capacity building training for HR and for establishment of and maintenance of enquiry points; • Support on building institutional mechanism for the functioning of the EP; mandate, procedures, fees; position for the services of the EP within the designated government entity; • ICT infrastructure and technology for maintaining enquiry points and creating database of requests and information provided, etc.; • Awareness raising for the private sector on communication with enquiry points. | Information and communication technologies (ICT), Legislative and regulatory framework, Infrastructure and equipment, Human resources and training, Awareness-raising
2.1 | 2.1.1, 2.1.2, 2.1.3 | Comments and information before entry into force | 31 December 2019 | 22 August 2023 | Yes | No |  | • Legal support on designing, drafting of legislative changes and necessary regulations, SoP, etc.; • Staff capacity building on developing procedures; managing notification and public comment on proposed laws and regulations; • Technical assistance and capacity building and training for HR on managing notification and public comment on proposed laws and regulations; • Institutional support for establishment of efficient standing body, engaging traders’ associations, creation of a single mechanism for providing and receiving comments and effective publishing of information, etc.; • Awareness raising for the private sector on a new instrument and modalities for comments. | Information and communication technologies (ICT), Legislative and regulatory framework, Human resources and training, Awareness-raising
2.2 | 2.2 | Consultations | 31 December 2022 | 22 August 2023 | Yes | No |  | • Technical assistance and capacity building and HR training for developing public consultation strategy, procedures and on carrying out consultations; • Legal support, including design, drafting of legislative changes and necessary regulations, SoP, etc.; • Awareness raising for the private sector on consultation mechanism. | Legislative and regulatory framework, Human resources and training, Awareness-raising
3 | 3.1, 3.2 (a), 3.2 (b), 3.3, 3.4, 3.5, 3.6 (a), 3.6 (b), 3.6 (c), 3.7, 3.8, 3.9 (a) (i), 3.9 (a) (ii), 3.9 (b) (i), 3.9 (b) (ii), 3.9 (b) (iii), 3.9 (b) (iv), 3.9 (c), 3.9 (d) | Advance rulings | 31 December 2019 | 22 August 2023 | Yes | No |  | • Technical assistance and capacity building for advance rulings implementation; • Legal support on designing, drafting of legislative changes and necessary regulations, SoP, etc.; • Equipment/technology for upgrading the laboratories; • Awareness raising for the private sector on advance rulings mechanism. | Information and communication technologies (ICT), Legislative and regulatory framework, Infrastructure and equipment, Human resources and training, Awareness-raising
5.1 | 5.1 (a), 5.1 (b), 5.1 (c), 5.1 (d) | Notifications for enhanced controls or inspections | 31 December 2023 | 22 August 2023 | Yes | No |  | • Legal support on designing, drafting of legislative changes and necessary regulations, SoP, etc.; • Technical assistance on the design and establishment of a notification system for enhanced controls or inspections; • Capacity building and HR training on implementing a notification system for enhanced controls or inspections; • ICT Infrastructure for establishing an automated notification system. | Information and communication technologies (ICT), Legislative and regulatory framework, Infrastructure and equipment, Human resources and training
5.3 | 5.3.1, 5.3.2, 5.3.3 | Test procedures | 31 December 2022 | 22 August 2023 | Yes | No |  | • Legal support on designing, drafting of legislative changes and necessary regulations, SoP, etc.; • Testing kits and other relevant laboratory equipment/materials; • Technical support to develop testing parameters and accreditation for veterinary laboratories; • ICT infrastructure, soft infrastructure (networking, automation, high-speed internet). | Information and communication technologies (ICT), Legislative and regulatory framework, Infrastructure and equipment, Human resources and training
7.1 | 7.1.1, 7.1.2 | Pre-arrival processing | 31 December 2024 | 22 August 2023 | Yes | No |  | • Technical assistance, capacity building and Hr training on pre –arrival processing, including required changes in the clearance procedure, changes in ASYCUDA and in risk management; • Awareness raising for the private sector on pre-arrival processing mechanism; • Legal support on designing, drafting of legislative changes and necessary regulations, SoP, etc. | Information and communication technologies (ICT), Legislative and regulatory framework, Human resources and training, Awareness-raising
7.2 | 7.2 | Electronic payment | 31 December 2024 | 22 August 2023 | Yes | No |  | • Technical assistance on the design and establishment of an electronic payment system; • ICT Infrastructure and equipment for enabling the system. | Information and communication technologies (ICT), Infrastructure and equipment
7.4 | 7.4.1, 7.4.2, 7.4.3, 7.4.4 | Risk management | 31 December 2024 | 22 August 2023 | Yes | No |  | • Legal support on designing, drafting of legislative changes and necessary regulations, SoP, etc.; • Technical assistance on the design and establishment of a risk management system; • ICT Infrastructure and equipment for an automated risk management system; • Capacity building and HR training on implementing the risk management system. | Information and communication technologies (ICT), Legislative and regulatory framework, Infrastructure and equipment, Human resources and training
7.5 | 7.5.1, 7.5.2, 7.5.3, 7.5.4 | Post-clearance audit | 31 December 2024 | 22 August 2023 | Yes | No |  | • Legal support on designing, drafting of legislative changes and necessary regulations, SoP, etc.; • Technical assistance for mainstreaming of Post Clearance Audit into daily operations; • Capacity building and HR training. | Legislative and regulatory framework, Human resources and training
7.6 | 7.6.1, 7.6.2 | Average release times | 31 December 2024 | 22 August 2023 | Yes | No |  | • Technical assistance and capacity building and HR training on designing, planning and implementing TRS, including on building methodology, testing it and making it sustainable. | Legislative and regulatory framework, Human resources and training
7.7 | 7.7.1, 7.7.2 (a) (i), 7.7.2 (a) (ii), 7.7.2 (a) (iii), 7.7.2 (a) (iv), 7.7.2 (b) (i), 7.7.2 (b) (ii), 7.7.3 (a), 7.7.3 (b), 7.7.3 (c), 7.7.3 (d), 7.7.3 (e), 7.7.3 (f), 7.7.3 (g), 7.7.4, 7.7.5, 7.7.6 | Authorized operators | 31 December 2024 | 22 August 2023 | Yes | No |  | • Legal support on designing, drafting of legislative changes and necessary regulations, SoP, etc.; • Technical assistance and capacity building, HR training on design, implementation and review of authorized trader scheme, audit abilities • Awareness raising for the private sector on application of the scheme | Legislative and regulatory framework, Human resources and training, Awareness-raising
7.8 | 7.8.1 (a), 7.8.1 (b), 7.8.1 (c), 7.8.1 (d), 7.8.1 (e), 7.8.1 (f), 7.8.1 (g), 7.8.1 (h), 7.8.2 (a), 7.8.2 (b), 7.8.2 (c), 7.8.2 (d), 7.8.3 | Expedited shipments | 31 December 2022 | 22 August 2023 | Yes | No |  | • Legal support on designing, drafting of legislative changes and necessary regulations, SoP, etc.; • Equipment and facilities for express cargo inspection. | Legislative and regulatory framework, Infrastructure and equipment
8 | 8.1, 8.2 (a), 8.2 (b), 8.2 (c), 8.2 (d), 8.2 (e) | Border Agency Cooperation | 31 December 2027 | 22 August 2023 | Yes | No |  | • Legal support on designing, drafting of legislative changes and necessary regulations, agreements, SoP, etc.; • Technical assistance for putting in place technical arrangements for sharing of data and information, developing a strategy/framework for border agency cooperation; • Capacity building and HR training on border agency cooperation and share of best practices; • Equipment and facilities for border crossing points. | Information and communication technologies (ICT), Legislative and regulatory framework, Infrastructure and equipment, Institutional procedures, Human resources and training
10.2 | 10.2.1, 10.2.2, 10.2.3 | Acceptance of copies | 31 December 2022 | 22 August 2023 | Yes | No |  | • Legal support on designing, drafting of legislative changes and necessary regulations, agreements, SoP, etc.; • Technical assistance on developing a system for periodic review of formalities and documentation requirements; • ICT infrastructure, technology and equipment for border agencies and government agencies; • Capacity building of HR on the benefits of electronic documentation and processes and treatment of copies; • Awareness raising for the private sector. | Information and communication technologies (ICT), Legislative and regulatory framework, Infrastructure and equipment, Human resources and training, Awareness-raising
10.3 | 10.3.1, 10.3.2 | Use of international standards | 31 December 2027 | 22 August 2023 | Yes | No |  | • Legal support on designing, drafting of legislative changes and necessary regulations, agreements, SoP, etc.; • Technical assistance, capacity building, HR training on the relevant international standards, testing procedures and international best practices. | Legislative and regulatory framework, Human resources and training
10.4 | 10.4.1, 10.4.2, 10.4.3, 10.4.4 | Single window | 31 December 2027 | 22 August 2023 | Yes | No |  | • Legal support on designing, drafting of legislative changes and necessary regulations, agreements, SoP, etc.; • Technical assistance in developing a comprehensive and operational SW system • ICT Infrastructure and equipment for automation at each agency; • ICT infrastructure and equipment for SW; • Capacity building and training of HR on the use and implementation of SW; • Awareness raising and capacity building for the private sector on the effective use of SW. | Information and communication technologies (ICT), Legislative and regulatory framework, Infrastructure and equipment, Human resources and training, Awareness-raising
11 | 11.5 | Transit | 31 December 2027 | 22 August 2023 | Yes | No |  | • Physical infrastructure | Infrastructure and equipment
11 | 11.9 | Transit | 31 December 2027 | 22 August 2023 | Yes | No |  | • Technical assistance, capacity building and Hr training on pre –arrival processing, including required changes in the clearance procedure, changes in ASYCUDA and in risk management; • Awareness raising for the private sector on pre-arrival processing mechanism; • Legal support on designing, drafting of legislative changes and necessary regulations, SoP, etc. | Information and communication technologies (ICT), Legislative and regulatory framework, Human resources and training, Awareness-raising
12 | 12.2.1, 12.2.2, 12.3, 12.4.1 (a), 12.4.1 (b), 12.4.1 (c), 12.4.1 (d), 12.4.1 (e), 12.4.1 (f), 12.4.2, 12.5.1 (a), 12.5.1 (b), 12.5.1 (c), 12.5.1 (d), 12.5.1 (e), 12.5.1 (f), 12.5.2, 12.5.3, 12.6.1 (a), 12.6.1 (b), 12.6.1 (c), 12.6.1 (d), 12.6.1 (e), 12.6.2, 12.7.1 (a), 12.7.1 (b), 12.7.1 (c), 12.7.1 (d), 12.7.1 (e), 12.7.2, 12.8, 12.9.1, 12.9.2, 12.10 (a), 12.10 (b), 12.10 (c), 12.10 (d), 12.10 (e), 12.10 (f), 12.10 (g), 12.10 (h), 12.11.1 (a), 12.11.1 (b), 12.11.1 (c), 12.11.2, 12.12.1, 12.12.2 | Customs cooperation | 31 December 2027 | 22 August 2023 | Yes | No |  | • Legal support on drafting agreements; • Technical assistance and capacity building on best practices in customs cooperation and drafting the agreements. | Legislative and regulatory framework, Human resources and training