## Worksheet
Measure | Items | Measure name | Indicative Implementation Date | Definitive Implementation Date | TA needs notified | Progress reported | Donor / Agency | TA Description | Tags
1.1 | 1.1.1 | Publication | 31 December 2025 | 01 January 2035 | No | No |  | Legal expertise to update/draft relevant legislation • Assistance to formulate written policy between government departments that regulates the publication of information • Technical assistance to translate information into other WTO languages as well as Mandarin, as appropriate • Training of human resource in the relevant ministries and departments inclusive of the Ministry of Information • Develop a sustainable platform to address security concerns • Assistance to publish information in a timely manner; to be user friendly etc. rulings on the classification or valuation of products for customs purposes • Assistance to review Agreements or parts thereof with any country or countries relating to importation and exportation or transit • Develop administrative procedures relating to the imposition on tariff quotas to be made readily available • Develop a strategic approach to the publication of trade related information to allow for access in an easy and reliable manner – Legislations (tariffs, fees, import and export procedure) • Coordinate an approach to disseminate information between relevant agencies in a timely manner | Information and communication technologies (ICT), Legislative and regulatory framework, Institutional procedures, Human resources and training, Awareness-raising
1.2 | 1.2 | Information available through internet | 31 December 2030 | 01 January 2035 | No | No |  | • Legal expertise to develop legislations • Develop a comprehensive information technology (IT) strategy system • Technical assistance related to ITC hardware and software setting • Training of staff and additional human resource is required to deal with the task of the issue of monitoring laws online • Assistance to create/update an information management system • Implement web-publication policy and guidelines • Assistance to develop security and protection of domain • Develop mechanism to determine funding for continuous hosting of website | Information and communication technologies (ICT), Legislative and regulatory framework, Human resources and training
1.3 | 1.3 | Enquiry points | 31 December 2030 | 01 January 2035 | No | No |  | • Establish a central enquiry point • Designate satellite departments to act as representative disciplines such as: Ministry of Foreign Affairs, Bureau of Standards, Ministry of Trade, Ministry of Agriculture, Plant Protection Unit, Ministry of Health • Establish a sustainable network to receive and disseminate information • Develop a coordinated approach to handle enquiries in a timely manner • Training of human resource to monitor and disseminate information to other government agencies • Financial assistance and technical advice for certain government agencies and departments with limited financial and human resources | Information and communication technologies (ICT), Human resources and training
2.2 | 2.2 | Consultations | 31 December 2025 | 01 January 2030 | No | No |  | • Develop relevant Legal and Administrative document that deals with policy on consultation and procedures • Assistance to establish a formalised mechanism to facilitate consultations on a regular basis which involves; 1. Inviting the private sector into the NTFC 2. Conducting surveys to collect information on trade-related procedures and sharing findings with the public and consultations; and 3. Collaboration with the technicians as well as the legal team from different ministries. | Information and communication technologies (ICT), Legislative and regulatory framework, Institutional procedures
3 | 3 | Advance rulings | 31 December 2025 | 01 January 2038 | No | No |  | • Assistance to develop relevant laws and administrative procedures • Establish a process to facilitate the continuous update of content • Technical assistance to regularly update tariff classification and valuation • Provide ICT technical support to ensure that publications are always accessible in an easy manner • Training of personnel assigned to the task • Establish procedure for making and processing request | Information and communication technologies (ICT), Legislative and regulatory framework, Human resources and training
5.3 | 5.3 | Test procedures | 31 December 2030 | 01 January 2034 | No | No |  | • Develop required legislation • Review of administrative procedure • Draft legal or administrative procedure for second testing • Establish a laboratory accreditation program (human and financial resources) • Establish accredited list of laboratories • Training of human resource to build technical capacity • Financial assistance to allocate financial resources for infrastructure and equipment development for testing facilities • Procedure to ascertain cost for services rendered | Information and communication technologies (ICT), Legislative and regulatory framework, Institutional procedures, Human resources and training
6.1 | 6.1 | General disciplines on fees and charges | 31 December 2031 | 01 January 2035 | No | No |  | • Technical assistance to update legislation • Policy guidance to analyse existing fees and reasons for adjusting • Assistance to draft guidelines for levying charge • Categorizing of services charged • Procedure to ascertain cost for each of these services rendered • Regularly update information | Information and communication technologies (ICT), Legislative and regulatory framework, Diagnostic and Needs Assessment
6.2 | 6.2 | Specific disciplines on fees and charges | 31 December 2031 | 01 January 2035 | No | No |  | • Reliable update mechanism to analyse existing fees and reasons for adjustment • Drafting guidelines for levying charge • Categorize services charged • Ascertain cost for each of these services rendered • Regular update of information | Information and communication technologies (ICT), Legislative and regulatory framework
7.4 | 7.4 | Risk management | 31 December 2031 | 01 January 2035 | No | No |  | • Technical assistance to establish a framework that would encourage collaboration amongst relevant agencies such as the Bureau of Standards, Plant Protection, Ministry of Health and Customs Department and Custom Brokers • Technical assistance to develop a sustainable ICT framework such as portal • Training of human resource to improve Customs operations • Assistance to train and sensitize customs brokers • Technical assistance required for infrastructural and equipment upgrade to border | Information and communication technologies (ICT), Legislative and regulatory framework, Infrastructure and equipment, Institutional procedures, Human resources and training
7.6 | 7.6 | Average release times | 31 December 2030 | 01 January 2035 | No | No |  | • Technical assistance to establish and have access to average release time • Training of human resource to improve capacity of borders agencies to accomplish task • Assistance to train and sensitize custom brokers • Establish a portal link to ASYCUDA WORLD, since multiple agencies are involved, verification must be done with all | Information and communication technologies (ICT), Legislative and regulatory framework, Human resources and training, Awareness-raising
7.7 | 7.7 | Authorized operators | 31 December 2031 | 01 January 2035 | No | No |  | • Legal expertise to update/draft the relevant legislation • Assistance required to develop accurate record keeping and readily availability of information • Establish a system to encourage coordination among stakeholders • Create a single window for declaration for all imports or exports in a given period; to encourage fewer physical inspections and examinations • Formalization of a regulatory framework for authorized operators • Establish mechanism of specific warehouses that are secured • Develop criteria that would be designated specific to trusted trader • Training of human resource, to improve Customs operations | Information and communication technologies (ICT), Legislative and regulatory framework, Human resources and training
10.4 | 10.4 | Single window | 31 December 2031 | 01 January 2035 | No | No |  | • Assistance to develop harmonize legislation • Establish coordination between border agency • Technical assistance to build capacity – training human resource • Identify and maintain a framework which encourage confidentiality • Develop and update of IT systems • Provide ICT technical support to ensure IT networking integration • Financial assistance to support infrastructure | Information and communication technologies (ICT), Legislative and regulatory framework, Infrastructure and equipment, Institutional procedures, Human resources and training
10.8 | 10.8.1 | Rejected Goods | 31 December 2031 | 01 January 2036 | No | No |  | • Technical assistance to develop legal and regulatory framework to deal with rejected goods • Training of human resources technical capacity assigned to the task • Assistance to develop appropriate Customs procedure to build capacity to implement this measure | Legislative and regulatory framework, Institutional procedures, Human resources and training
12 | 12 | Customs cooperation | 31 December 2030 | 01 January 2034 | No | No |  | • Technical assistance to develop legal and regulatory policies to deal with Customs cooperate with each other in the region (required harmonized legislations) • Assistance to develop a physical agreement to establish a formal system; among multiple border agencies • Training of human resource to promote border coordination • Assistance to develop appropriate Customs procedure • Provide ICT technical support to ensure IT networking integration • This measure is currently being implemented (may be fully) as part of the WCO accession process • Financial assistance to support infrastructure and interconnectivity | Information and communication technologies (ICT), Legislative and regulatory framework, Infrastructure and equipment, Institutional procedures, Human resources and training