## Worksheet
Measure | Items | Measure name | Indicative Implementation Date | Definitive Implementation Date | TA needs notified | Progress reported | Donor / Agency | TA Description | Tags
1.2 | 1.2.1 (a), 1.2.1 (b), 1.2.1 (c), 1.2.2, 1.2.3 | Information available through internet | 30 September 2021 | 30 March 2027 | Yes | No |  | - Development and implementation of policy guidelines on publication of trade-related information; - Timely review and update of trade related information on Internet by the relevant agencies; - Creation of a trade information portal; - Institutional capacity building. | Information and communication technologies (ICT), Legislative and regulatory framework, Institutional procedures
2.2 | 2.2 | Consultations | 30 November 2020 | 30 May 2027 | Yes | No |  | - Technical assistance to develop a consultation policy, particularly with respect to developing skills in regulatory impact assessment; - Technical consultancy to develop the strategy/policy for consultations and designate unit for implementation; - Legal counsel to define a standardized approach to consultations. | Legislative and regulatory framework, Diagnostic and Needs Assessment
6.2 | 6.2 (i), 6.2 (ii) | Specific disciplines on fees and charges | 30 November 2020 | 30 May 2027 | Yes | No |  | - Drafting/amending all applicable legislation, including the Finance Law, the Foreign Trade Law and the Customs and Excise Administration Law, in order to apply the customs user fee; - Assistance to develop relevant procedures in order to establish and effectively apply the customs user fee. | Legislative and regulatory framework, Institutional procedures
7.2 | 7.2 | Electronic payment | 31 December 2022 | 31 December 2024 | Yes | No |  | - Preparation of the strategic document for the development of e-payment; - Development of e-payment solutions (all banks); - Establishment of technical and financial support measures in digital sectors relating to e commerce (training, research); - Enhancement of the current functionalities of the single window for cross-border operations (GUOT) or the single window for customs clearance (GUD); - Quality improvement of Internet connection; - Legislative drafting/amending of all e-legislation and the Finance Law in order to undertake electronic payment. | Information and communication technologies (ICT), Legislative and regulatory framework, Infrastructure and equipment, Human resources and training
7.3 | 7.3.1, 7.3.2 (a), 7.3.2 (b), 7.3.3, 7.3.4, 7.3.5, 7.3.6 | Separation of release | 30 November 2020 | 31 December 2024 | Yes | No |  | - Carrying out a technical/legal diagnosis; - Preparing regulations to enable application of this rule; - Adapting or developing the IT systems of relevant agencies; - Defining procedures for users and implementing agencies; - Dissemination and training. | Information and communication technologies (ICT), Legislative and regulatory framework, Diagnostic and Needs Assessment, Institutional procedures, Awareness-raising
7.4 | 7.4.1, 7.4.2, 7.4.3, 7.4.4 | Risk management | 30 September 2020 | 30 March 2027 | Yes | No |  | - Technical assistance required to develop a mechanism to ensure enhanced coordination and collaboration between border agencies on risk identification and application of risk management; - Technical assistance to develop procedures required for effective implementation of risk management system; - Technical assistance to develop capacity in relevant border agencies to have a full understanding and application of risk management system; - Assistance required to acquire as well as enhance technological capabilities necessary to implement a proper risk management process; - Assistance to deploy technology required to implement a proper risk management system, such as X-ray machines, scanners and laboratory testing facilities; - Technical assistance required to train customs personnel in imaging. | Information and communication technologies (ICT), Legislative and regulatory framework, Infrastructure and equipment, Institutional procedures, Human resources and training
7.6 | 7.6.1, 7.6.2 | Average release times | 31 October 2021 | 30 April 2027 | Yes | No |  | - Preparation of a study on average release times (guide to measure the average time required for the release of goods). | Diagnostic and Needs Assessment
7.8 | 7.8.1 (a), 7.8.1 (b), 7.8.1 (c), 7.8.1 (d), 7.8.1 (e), 7.8.1 (f), 7.8.1 (g), 7.8.1 (h), 7.8.2 (a), 7.8.2 (b), 7.8.2 (c), 7.8.2 (d), 7.8.3 | Expedited shipments | 30 September 2020 | 30 March 2027 | Yes | No |  | - Support to review the legislation on urgent consignments and extend its scope to other goods; - Support for capacity building/coaching of border agency officials. | Legislative and regulatory framework, Institutional procedures, Human resources and training
8 | 8.1, 8.2 (a), 8.2 (b), 8.2 (c), 8.2 (d), 8.2 (e) | Border Agency Cooperation | 31 December 2020 | 30 June 2027 | Yes | No |  | - Revision of current goods import, export or transit formalities and procedures at border crossings; - Preparation of a harmonized border procedures manual; - Interconnection of other customs units (customs posts and brigades in the interior) with the customs systems; - Training border agency officials in and raising their awareness of new cooperation practices. | Information and communication technologies (ICT), Legislative and regulatory framework, Human resources and training, Awareness-raising
10.1 | 10.1.1 (a), 10.1.1 (b), 10.1.1 (c), 10.1.1 (d) | Formalities | 30 October 2021 | 31 December 2024 | Yes | No |  | - Assistance to analyse and simplify documentation requirements and procedures; - Capacity building and training in formalities and required documents in line with international best practices. | Legislative and regulatory framework, Human resources and training
10.4 | 10.4.1, 10.4.2, 10.4.3, 10.4.4 | Single window | 30 September 2021 | 31 December 2024 | Yes | No |  | - Technical assistance required to recast the operations of the single window for cross-border operations (GUOT); - Technical assistance required to unify the two single windows (GUD and GUOT); - Development of efficient procedures and a checklist in order to implement a national single window effectively; - Technical assistance to build capacity in relevant border agencies in order to implement a national single window; - Capacity building assistance to raise the awareness of officials of relevant border agencies and businesses and to equip and train them in order to implement a national single window; - Assistance to ensure reasonable- to high-level Internet access and access to ICT equipment, especially for other border agencies; - Technical assistance required to train agents involved in managing juxtaposed offices at the borders. | Information and communication technologies (ICT), Legislative and regulatory framework, Infrastructure and equipment, Human resources and training, Awareness-raising
10.5 | 10.5.1, 10.5.2 | Preshipment inspection | 31 December 2021 | 31 December 2024 | Yes | No |  | - Assistance to train customs officers in scanner management techniques; - Assistance to transfer responsibility from preshipment inspection agencies to customs officers; - Assistance to train customs personnel in valuation and rates. | Human resources and training
11 | 11.1 (a), 11.1 (b), 11.2, 11.3 | Transit | 30 December 2020 | 30 December 2024 | Yes | No |  | - Technical assistance and capacity building support are required to:  ensure proper allocation of costs  train personnel. | Human resources and training
11 | 11.5 | Transit | 30 December 2020 | 31 December 2024 | Yes | No |  | - Technical assistance required to set up infrastructure to facilitate the movement of goods:  Support for corridor monitoring exercises  Training on treatment of goods in transit  Analysis of an efficient transit system  Construction of a dry port for transit purposes  Construction of warehouses for goods in transit  Construction of parking areas for vehicles in transit. | Infrastructure and equipment, Human resources and training
11 | 11.6 (a), 11.6 (b) | Transit | 30 December 2020 | 31 December 2024 | Yes | No |  | - Technical assistance required to set up infrastructure to facilitate the movement of goods:  Support for corridor monitoring exercises  Training on treatment of goods in transit  Analysis of an efficient transit system  Construction of a dry port for transit purposes  Construction of warehouses for goods in transit  Construction of parking areas for vehicles in transit. | Human resources and training, Infrastructure and equipment
11 | 11.7 | Transit | 30 December 2020 | 31 December 2024 | Yes | No |  | - Technical assistance required to set up infrastructure to facilitate the movement of goods:  Support for corridor monitoring exercises  Training on treatment of goods in transit  Analysis of an efficient transit system  Construction of a dry port for transit purposes  Construction of warehouses for goods in transit  Construction of parking areas for vehicles in transit. | Human resources and training, Infrastructure and equipment
11 | 11.8 | Transit | 30 December 2020 | 31 December 2024 | Yes | No |  | - Technical assistance required to set up infrastructure to facilitate the movement of goods:  Support for corridor monitoring exercises  Training on treatment of goods in transit  Analysis of an efficient transit system  Construction of a dry port for transit purposes  Construction of warehouses for goods in transit  Construction of parking areas for vehicles in transit. | Human resources and training, Infrastructure and equipment
11 | 11.9 | Transit | 30 December 2020 | 31 December 2024 | Yes | No |  | - Technical assistance required to set up infrastructure to facilitate the movement of goods:  Support for corridor monitoring exercises  Training on treatment of goods in transit  Analysis of an efficient transit system  Construction of a dry port for transit purposes  Construction of warehouses for goods in transit  Construction of parking areas for vehicles in transit. | Human resources and training, Infrastructure and equipment
11 | 11.1 | Transit | 30 December 2020 | 31 December 2024 | Yes | No |  | - Technical assistance required to set up infrastructure to facilitate the movement of goods:  Support for corridor monitoring exercises  Training on treatment of goods in transit  Analysis of an efficient transit system  Construction of a dry port for transit purposes  Construction of warehouses for goods in transit  Construction of parking areas for vehicles in transit. | Human resources and training, Infrastructure and equipment
11 | 11.11 | Transit | 30 December 2020 | 30 December 2025 | Yes | No |  | - Training in cooperation and coordination among regulatory agencies; - Customs transit procedures. | Legislative and regulatory framework, Human resources and training