## Worksheet
Measure | Items | Measure name | Indicative Implementation Date | Definitive Implementation Date | TA needs notified | Progress reported | Donor / Agency | TA Description | Tags
1.1 | 1.1.1 (a), 1.1.1 (b), 1.1.1 (c), 1.1.1 (d), 1.1.1 (e), 1.1.1 (f), 1.1.1 (g), 1.1.1 (h), 1.1.1 (i), 1.1.1 (j) | Publication | 31 December 2024 | 31 December 2027 | Yes | No |  | Technical and financial assistance: Project (1): Establishment of the information system relating to the Agreement on Trade Facilitation (TFA)  Assign responsibility for information management project to the Minister of Trade (measure 39);  Produce information to be provided and check that it is user friendly and readable;  Revise legal framework to ensure legal validity and authenticity of information provided;  Define and organize provision of information (different aspects of publication media and outlets, information technology, maintenance, storage and publication of information);  Adopt organizational framework to supervise maintenance of information and establish institutional responsibilities, together with policies or rules, including security rules;  Recruit additional human resources;  Carry out training and capacity building. | Information and communication technologies (ICT), Legislative and regulatory framework, Human resources and training
1.2 | 1.2.1 (a), 1.2.1 (b), 1.2.1 (c), 1.2.2, 1.2.3 | Information available through internet | 31 December 2024 | 31 December 2027 | Yes | No |  | Technical and financial assistance: Project (1): Establishment of the information system relating to the Agreement on Trade Facilitation (TFA)  Assign to National Trade Facilitation Committee (measure 39) the task of drawing up an inventory of relevant projects that might facilitate implementation of this measure;  Revise legal framework to ensure legal validity and authenticity of information provided;  Define and organize provision of information (different aspects of publication media and outlets, information technology, maintenance, storage and publication of information);  Adopt organizational framework to supervise maintenance of information and establish institutional responsibilities;  Ensure systematic use of information and communication technologies (ICTs);  Carry out training and capacity building;  Provide adequate equipment. | Information and communication technologies (ICT), Legislative and regulatory framework, Infrastructure and equipment, Human resources and training
1.3 | 1.3.1, 1.3.2, 1.3.3, 1.3.4 | Enquiry points | 31 December 2024 | 31 December 2027 | Yes | No |  | Technical and financial assistance: Project (1): Establishment of the information system relating to the Agreement on Trade Facilitation (TFA) Estimated cost of project: 272.79 million CFA francs  Establish mechanism for coordination with other agencies, with required cooperation and provision of information (including changing the legal or regulatory framework);  Hold training for staff who will provide the service;  Establish guidelines covering all stages from receiving enquiry to sending reply;  Develop use of standardized communications;  Establish quality control standards and procedures, including deadline for sending replies;  Ensure systematic use of ICTs;  Provide adequate equipment. | Information and communication technologies (ICT), Legislative and regulatory framework, Infrastructure and equipment, Institutional procedures, Human resources and training
1.4 | 1.4 (a), 1.4 (b), 1.4 (c) | Notification | 31 December 2024 | 31 December 2027 | Yes | No |  | Establish enquiry points. | Information and communication technologies (ICT)
3 | 3.1, 3.2 (a), 3.2 (b), 3.3, 3.4, 3.5, 3.6 (a), 3.6 (b), 3.6 (c), 3.7, 3.8, 3.9 (a) (i), 3.9 (a) (ii), 3.9 (b) (i), 3.9 (b) (ii), 3.9 (b) (iii), 3.9 (b) (iv), 3.9 (c), 3.9 (d) | Advance rulings | 31 December 2022 | 31 December 2027 | Yes | No |  | Technical and financial assistance: Project (4): Establishment of an operational unit responsible for issuing advance rulings at the Directorate-General of Customs and Indirect Taxation Estimated cost of project: 191.1 million CFA francs  Create specialist unit or section at Directorate-General of Customs for processing of advance rulings;  Establish procedures for making and processing an application (legal and regulatory framework);  Carry out training and capacity building (processing of advance rulings, harmonized system);  Establish database on advance rulings;  Create customs laboratory;  Improve national structure for classification work (see WCO study);  Ensure systematic use of ICTs;  Provide adequate equipment. | Information and communication technologies (ICT), Legislative and regulatory framework, Infrastructure and equipment, Institutional procedures
4 | 4.1 (a), 4.1 (b), 4.2, 4.3, 4.4 (a), 4.4 (b), 4.4 end paragraph, 4.5, 4.6 | Procedures for appeal or review | 31 December 2022 | 31 December 2027 | Yes | No |  |  Revise legal framework to incorporate provisions on appeal time limits and procedures;  Revise legal framework (CEMAC) to incorporate provisions on appeal time limits and procedures. | Legislative and regulatory framework, Diagnostic and Needs Assessment
5.1 | 5.1 (a), 5.1 (b), 5.1 (c), 5.1 (d) | Notifications for enhanced controls or inspections | 31 December 2024 | 31 December 2031 | Yes | No |  | Technical and financial assistance: Project (5): Establishment of a secure system for the importation and exportation of goods in Gabon Estimated cost of project: 218.4 million CFA francs | Information and communication technologies (ICT)
5.3 | 5.3.1, 5.3.2, 5.3.3 | Test procedures | 31 December 2023 | 31 December 2028 | Yes | No |  | Technical and financial assistance: Project (5): Establishment of a secure system for the importation and exportation of goods in Gabon  Set up an accredited multi sectoral national laboratory;  Obtain ISO certification for other existing laboratories (livestock, consumption, …);  Provide support for veterinary diagnostic laboratory in establishing quality assurance system for purposes of accreditation;  Help with collection of samples needed for tests;  Provide laboratory with aid fund to cover cost of taking samples from livestock;  Change legal or regulatory framework;  Ensure systematic use of ICTs;  Recruit additional human resources;  Carry out training and capacity building for specialist staff (training of employees in specialist schools for biology, chemistry, physics, etc.);  Provide adequate equipment;  Conduct audits of import procedures and processes, particularly inspection of food products, with the assistance of tools or recommendations of relevant international organizations for upgrading the regulatory framework and procedures;  Establish a strategic and operational framework for border agency collaboration;  Computerize formalities relating to sanitary and phytosanitary control procedures and food controls. | Information and communication technologies (ICT), Legislative and regulatory framework, Infrastructure and equipment, Diagnostic and Needs Assessment, Institutional procedures, Human resources and training
6.1 | 6.1.1, 6.1.2, 6.1.3, 6.1.4 | General disciplines on fees and charges | 31 December 2022 | 31 December 2027 | Yes | No |  |  Conduct analysis of importation and exportation fees and charges to determine those that are ad valorem or the amount of which does not correspond to the cost of services rendered;  Establish system for calculating real cost of procedures and documents supplied;  Train staff in implementation of changes in procedures for collection of fees and charges. | Information and communication technologies (ICT), Diagnostic and Needs Assessment, Human resources and training
6.2 | 6.2 (i), 6.2 (ii) | Specific disciplines on fees and charges | 31 December 2022 | 31 December 2027 | Yes | No |  | Revision of CEMAC Customs Code. | Legislative and regulatory framework
6.3 | 6.3.1, 6.3.2, 6.3.3, 6.3.4 (a), 6.3.4 (b), 6.3.5, 6.3.6, 6.3.7 | Penalty Disciplines | 31 December 2022 | 31 December 2027 | Yes | No |  | Revamp Customs Code to incorporate new provisions. | Information and communication technologies (ICT), Legislative and regulatory framework
7.3 | 7.3.1, 7.3.2 (a), 7.3.2 (b), 7.3.3, 7.3.4, 7.3.5, 7.3.6 | Separation of release | 31 December 2022 | 31 December 2027 | Yes | No |  | Formalize current procedure (amend CEMAC Customs Code). | Legislative and regulatory framework
7.4 | 7.4.1, 7.4.2, 7.4.3, 7.4.4 | Risk management | 31 December 2022 | 31 December 2027 | Yes | No |  | Technical and financial assistance: Project (2): Feasibility study for establishing a multi-sectoral national laboratory in Gabon Estimated cost of project: 99.75 million CFA francs  Provide specialist training for staff directly involved in the implementation and operation of new procedures, for example with the help of the WCO e-learning module;  Develop risk management strategy and strategic management plan;  Establish a specialist unit within the customs authority (risk management unit) to monitor the implementation and operation of the system for collecting, classifying and analysing data on importers and transporters using relevant databases (CEN at the WCO, national confiscation reports, data provided by other administrations in the context of the WCO Nairobi Convention or bilateral agreements);  Review the legislation and customs regulations to reflect the use of risk management techniques within legal limits;  Introduce the use of an electronic manifest aligned to international standards to enable the identification of high-risk cargos;  Implement data in the computerized system;  Provide adequate equipment. | Information and communication technologies (ICT), Legislative and regulatory framework, Infrastructure and equipment, Diagnostic and Needs Assessment, Human resources and training
7.5 | 7.5.1, 7.5.2, 7.5.3, 7.5.4 | Post-clearance audit | 31 December 2020 | 31 December 2023 | Yes | No |  | Technical and financial assistance: Project (7): Establish an operational unit responsible for post clearance audits at the Directorate-General of Customs and Indirect Taxation Estimated costs of project: 223.650 million CFA francs  Strategic planning (development of an auditing strategy and a clear, gradual process);  Capacity building (train customs staff to maximize efficiency of post-clearance audits, raise public awareness of analytical work needed to benefit from the system, provide training in accounting and auditing methods);  Establish system of records/reports to provide customs management with sufficient evidence of achievements of audit team;  Institute cooperation with traders (establish positive atmosphere of trust between traders and customs staff, since post clearance audits are often conducted on traders' premises);  Ensure systematic use of ICTs;  Recruit additional human resources and draw up a plan of training on auditing methods based on risk management for post-clearance auditing staff;  Establish and implement an internal procedure for sharing of information with operational units and risk management to avoid duplication and conflicts regarding areas of competence. | Information and communication technologies (ICT), Legislative and regulatory framework, Institutional procedures, Human resources and training, Awareness-raising
7.6 | 7.6.1, 7.6.2 | Average release times | 31 December 2021 | 31 December 2023 | Yes | No |  | Technical and financial assistance: Project (8): Implementation of a study to determine average release times Estimated cost of project: 110.145 million CFA francs  Carry out study on release of goods (WCO study);  Awareness-raising for other persons working at borders (shipping agents, stevedores, carriers, clearing agents, …);  Establish a focus group involving the customs authority and the different actors involved in the platform (in particular within the National Trade Facilitation Committee (measure 39)). | Diagnostic and Needs Assessment, Institutional procedures, Awareness-raising
7.7 | 7.7.1, 7.7.2 (a) (i), 7.7.2 (a) (ii), 7.7.2 (a) (iii), 7.7.2 (a) (iv), 7.7.2 (b) (i), 7.7.2 (b) (ii), 7.7.3 (a), 7.7.3 (b), 7.7.3 (c), 7.7.3 (d), 7.7.3 (e), 7.7.3 (f), 7.7.3 (g), 7.7.4, 7.7.5, 7.7.6 | Authorized operators | 31 December 2024 | 31 December 2028 | Yes | No |  | Assistance technique et financière: Projet 9) Mise en place d’un programme de facilitation pour les opérateurs économiques agrées Coût prévisionnel du projet : 173,250 millions de FCFA  Procéder à la formation et au renforcement des capacités sur la gestion des registres et archive en direction des entreprises; -Elaborer un programme de formation pour les sociétés privées sur les exigences de tenues des registres et archives. | Legislative and regulatory framework, Human resources and training, Awareness-raising
8 | 8.1, 8.2 (a), 8.2 (b), 8.2 (c), 8.2 (d), 8.2 (e) | Border Agency Cooperation | 31 December 2024 | 31 December 2031 | Yes | No |  |  Set up an inter-agency committee for relevant border administrations;  Map procedures, mandates and functioning of all existing entities;  Establish system for monitoring traffic and time periods to measure impact of change with real-time identification of possible bottlenecks at border posts;  Modernize legal framework for border agency cooperation;  Define governance model for adjacent border control posts, including financing modalities for construction, maintenance and operation of facilities. | Information and communication technologies (ICT), Legislative and regulatory framework, Institutional procedures
10.1 | 10.1.1 (a), 10.1.1 (b), 10.1.1 (c), 10.1.1 (d) | Formalities | 31 December 2022 | 31 December 2027 | Yes | No |  |  Assign role to National Trade Facilitation Committee (measure 39) of analysing trade procedures in force, required formalities and documentation, and trade and documentation practices;  Computerize data exchange procedures;  Carry out training and capacity building. | Legislative and regulatory framework, Diagnostic and Needs Assessment, Human resources and training
10.2 | 10.2.1, 10.2.2, 10.2.3 | Acceptance of copies | 31 December 2024 | 31 December 2031 | Yes | No |  | Awaiting publication of the new CEMAC Code to ensure application of this Article. | Legislative and regulatory framework
10.3 | 10.3.1, 10.3.2 | Use of international standards | 31 December 2022 | 31 December 2027 | Yes | No |  |  Establish baseline for measuring progress achieved on implementation of each measure;  Introduce a common standard for the transmission of data between the different computer systems of public and private operators;  Reinforce and expand participation in international meetings and sessions on the preparation and revision of standards;  Apply relevant conventions on this subject (Nairobi). | Information and communication technologies (ICT), Legislative and regulatory framework, Awareness-raising
10.4 | 10.4.1, 10.4.2, 10.4.3, 10.4.4 | Single window | 31 December 2026 | 31 December 2035 | Yes | No |  | Technical and financial assistance: Project (10): Study concerning the establishment of a Single Window for foreign trade Cost of project: 175.245 million CFA francs  Analyse the trade process;  Take the decision to share data between agencies and departments;  Raise awareness of all stakeholders regarding the project (see WCO compendium on the Single Window);  Reinforce ICTs and establish a computerized network system;  Modify the legal or regulatory framework;  Change the institutional and/or administrative structure;  Study the establishment of the Single Window;  Standardize import and export procedures;  Harmonize procedures with other border agencies;  Carry out training and capacity building;  Provide adequate equipment. | Information and communication technologies (ICT), Legislative and regulatory framework, Infrastructure and equipment, Diagnostic and Needs Assessment, Institutional procedures, Human resources and training, Awareness-raising
10.6 | 10.6.1, 10.6.2, 10.6.3 | Use of customs brokers | 31 December 2025 | 31 December 2030 | Yes | No |  |  Revamp and regulate the profession of clearing agent;  Return to application of the CEMAC Customs Code;  Remove Article 112(2) of the Customs Code. | Legislative and regulatory framework, Human resources and training
10.7 | 10.7.1, 10.7.2 (a), 10.7.2 (b), 10.7.2 (c), 10.7.2 (d), 10.7.2 (e) | Common border procedures | 31 December 2026 | 31 December 2031 | No | No
11 | 11.1 (a), 11.1 (b), 11.2, 11.3, 11.4, 11.5, 11.6 (a), 11.6 (b), 11.7, 11.8, 11.9, 11.10, 11.11, 11.12, 11.13, 11.14, 11.15, 11.16 (a), 11.16 (b), 11.16 (c), 11.17 | Transit | 31 December 2022 | 31 December 2027 | Yes | No |  | Amend the Customs Code. | Legislative and regulatory framework