## Worksheet
Measure | Items | Measure name | Indicative Implementation Date | Definitive Implementation Date | Technical Assistance needs notified | Progress reported | Donor / Agency | TA Description | Tags
1.3 | 1.3 | Enquiry points | 31 August 2024 | 31 August 2026 | No | Yes | USAID, UNCTAD, TMA | - Develop a Legal Framework for establishment of a One Stop Centre Enquiry Point - Develop an Operations Manual for the One Stop Centre Enquiry Point - Harmonize procedures from different enquiry points for running the One Stop Centre Enquiry Point - Establishment and Operationalization of a One Stop Centre Enquiry Point - Awareness (sensitization workshops, media talks, etc) - Training of National Enquiry Points & NTFC subcommittees | Legislative and regulatory framework, Human resources and training, Awareness-raising
5.3 | 5.3 | Test procedures | 31 August 2024 | 31 August 2026 | No | Yes | TMA, USAID, UNCTAD | - Design Formal Operational Guidelines and Legal Framework for conducting/undertaking the Second Test - Build Staff Capacity with Appropriate Skills (public and private sectors) on use of second tests - Develop and interlink Laboratory Information Management Systems to all laboratories identified for testing - Conduct a Gaps Assessment of the capacity of existing private laboratories for their accreditation to enable them to provide the 2nd test required under the TFA - Support in peer assessment and regional proficiency testing for 3 years - Support to the proficiency testing (PT) schemes at regional level | Information and communication technologies (ICT), Legislative and regulatory framework, Diagnostic and Needs Assessment, Human resources and training
7.4 | 7.4.3 | Risk management | 31 August 2024 | 31 August 2030 | No | Yes | TMA | - Risk Management System interface for agencies involved in export, import and transit (integrated risk management-through the eSW) - Build capacity for Staff of concerned Government institutions and Risk Management Committee - Procure laboratory equipment for various tests and other inspection tools - Establish and Operationalise the Risk Management Committee - Awareness of traders on Risk Management | Information and communication technologies (ICT), Legislative and regulatory framework, Infrastructure and equipment, Human resources and training, Awareness-raising
7.6 | 7.6 | Average release times | 31 August 2024 | 31 August 2029 | No | Yes | ITC, UNCTAD | Rwanda is submitting the notification to shift from category B to category C in order to obtain financial and technical assistance and capacity building support to carry out Time Release Studies. | Diagnostic and Needs Assessment, Human resources and training
8 | 8 | Border Agency Cooperation | 31 August 2024 | 31 August 2030 | No | Yes | European Union, World Bank, TMA | - Enhance coordinated border management by harmonizing procedures and formalities (extension of border working hours, harmonization of working hours, joint inspections, etc) - Improve Operationalization of Joint Border Committees - Continue with work on One Stop Border Posts and required equipment such as e-gates, IT facilities, etc - Conduct Training, Sensitization, and Workshops of Stakeholders | Information and communication technologies (ICT), Legislative and regulatory framework, Infrastructure and equipment, Human resources and training, Awareness-raising
10.6 | 10.6 | Use of customs brokers | 31 August 2024 | 31 August 2030 | No | Yes | USAID, UNCTAD | - Review and publish the licensing requirements - Consider a careful interpretation of article 145 of EAC CMA 2004 and amend it to cater for TF provision and requirement - To review the legal base to allow importers to clear goods without the use of clearing agents - Capacity building for importers & exporters - Establish a review team led by the RRA, but encompassing representatives from the Broker community and interested members of the import/export community to commence the process | Information and communication technologies (ICT), Legislative and regulatory framework, Human resources and training