## Worksheet
Measure | Items | Measure name | Indicative Implementation Date | Definitive Implementation Date | TA needs notified | Progress reported | Donor / Agency | TA Description | Tags
1.2 | 1.2.1 (a), 1.2.1 (b), 1.2.1 (c), 1.2.2, 1.2.3 | Information available through internet | 22 February 2019 | 31 December 2029 | Yes | Yes | Australia, New Zealand | Support to amalgamate all information into a trade portal for purpose of complying with Article 1 sub articles 2.1 and 2.3. | Information and communication technologies (ICT)
2.1 | 2.1.1, 2.1.2, 2.1.3 | Comments and information before entry into force | 22 February 2020 | 31 December 2024 | Yes | Yes |  | Support to establish a consultation mechanism and provide with legal basis e.g. legislation. | Legislative and regulatory framework, Institutional procedures
3 | 3.1, 3.2 (a), 3.2 (b), 3.3, 3.4, 3.5, 3.6 (a), 3.6 (b), 3.6 (c), 3.7, 3.8, 3.9 (a) (i), 3.9 (a) (ii), 3.9 (b) (i), 3.9 (b) (ii), 3.9 (b) (iii), 3.9 (b) (iv), 3.9 (c), 3.9 (d) | Advance rulings | 22 February 2019 | 31 December 2024 | Yes | Yes | Australia, New Zealand | Customs need establishment of the Legal Framework and need Capacity Building for staffs. | Legislative and regulatory framework, Human resources and training
5.3 | 5.3.1, 5.3.2, 5.3.3 | Test procedures | 22 February 2022 | 31 December 2029 | Yes | Yes |  | Customs Discussed and agreed to C as there is no procedures set in place for that requirement. | Legislative and regulatory framework, Institutional procedures
7.4 | 7.4.1, 7.4.2, 7.4.3, 7.4.4 | Risk management | 22 February 2018 | 31 December 2024 | Yes | Yes | WCO, Australia, New Zealand | Legal/Policy: • Technical assistance to develop a mechanism to ensure enhanced coordination and collaboration between border agencies on risk identification and application of risk management. Procedures: • Technical assistance to develop necessary procedures that ensures effective implementation of risk management system. Human Resources/Training: • Technical assistance to develop capacity in relevant border agencies to ensure understanding and application of risk assessment and risk management to allow for better risk identification, analysis, assessment and treatment. ICT: • Enhance technological capacity for border agencies necessary to implement the risk management system. Infrastructure/Equipment: • Provision of appropriate technology and equipment to support the implementation of a proper risk management system. | Information and communication technologies (ICT), Legislative and regulatory framework, Infrastructure and equipment, Human resources and training, Institutional procedures
7.5 | 7.5.1, 7.5.2, 7.5.3, 7.5.4 | Post-clearance audit | 22 February 2022 | 31 December 2024 | Yes | Yes | WCO | Technical assistance will be needed to develop processes and procedures that incorporate the following in all aspects of risk management: o Draft a cargo clearance policy and process incorporating a risk based framework and PCA using the RKC as a guide o Draft terms of reference for the risk management committee o Draft position description for staff involved in risk management and set up a risk management unit o Train Customs and Quarantine staff on analysing available transaction data from CMS and identifying criteria for high risk cargo o Develop risk profiles using available transaction data from CMS o Train Customs and Quarantine staff on implementation of a risk based approach in the clearance of cargo Technical assistance will be needed to develop processes and procedures that incorporate the following in all aspects of PCA: o Draft position description for staff involved in PCA and strengthen the PCA unit o Train Customs and Quarantine staff on analysing available transaction data from CMS and selecting entries/companies for desk audits and field audits o Train Customs and Quarantine staff on PCA o Draft and implement an awareness program to educate the trading community on the role of PCA and legislative requirements related to PCA | Legislative and regulatory framework, Institutional procedures, Human resources and training, Awareness-raising
7.6 | 7.6.1, 7.6.2 | Average release times | 22 February 2022 | 31 December 2024 | Yes | Yes | WCO, WB | Technical assistance to be provided to Customs to develop capacity to undertake periodic Time Release Studies (TRS). | Human resources and training
7.7 | 7.7.1, 7.7.2 (a) (i), 7.7.2 (a) (ii), 7.7.2 (a) (iii), 7.7.2 (a) (iv), 7.7.2 (b) (i), 7.7.2 (b) (ii), 7.7.3 (a), 7.7.3 (b), 7.7.3 (c), 7.7.3 (d), 7.7.3 (e), 7.7.3 (f), 7.7.3 (g), 7.7.4, 7.7.5, 7.7.6 | Authorized operators | 22 February 2022 | 31 December 2024 | Yes | Yes | WB | Technical assistance will be needed to develop processes and procedures that incorporate the following in all aspects of risk management: o Draft a cargo clearance policy and process incorporating a risk based framework and PCA using the RKC as a guide o Draft terms of reference for the risk management committee o Draft position description for staff involved in risk management and set up a risk management unit o Train Customs and Quarantine staff on analysing available transaction data from CMS and identifying criteria for high risk cargo o Develop risk profiles using available transaction data from CMS o Train Customs and Quarantine staff on implementation of a risk based approach in the clearance of cargo Technical assistance will be needed to develop processes and procedures that incorporate the following in all aspects of PCA: o Draft position description for staff involved in PCA and strengthen the PCA unit o Train Customs and Quarantine staff on analysing available transaction data from CMS and selecting entries/companies for desk audits and field audits o Train Customs and Quarantine staff on PCA o Draft and implement an awareness program to educate the trading community on the role of PCA and legislative requirements related to PCA | Legislative and regulatory framework, Institutional procedures, Human resources and training, Awareness-raising
8 | 8.1, 8.2 (a), 8.2 (b), 8.2 (c), 8.2 (d), 8.2 (e) | Border Agency Cooperation | 22 February 2018 | 31 December 2024 | Yes | Yes | WCO | Procedures: • Support on developing a framework for border agency cooperation; draw up of a harmonized border procedures manual for border agencies. • Preparation of texts establishing and organizing joint controls and one-stop border post control. Human Resources/Training: • Support for staff on border agency cooperation. • Training in and awareness-raising of new cooperation practices for border agency officials. | Legislative and regulatory framework, Institutional procedures, Human resources and training, Awareness-raising
10.1 | 10.1.1 (a), 10.1.1 (b), 10.1.1 (c), 10.1.1 (d) | Formalities | 22 February 2020 | 31 December 2024 | Yes | Yes | Australia, New Zealand | Support to develop policy and legislative framework. | Legislative and regulatory framework
10.2 | 10.2.1, 10.2.2, 10.2.3 | Acceptance of copies | 22 February 2018 | 31 December 2024 | Yes | Yes |  | Support to develop policy and legislative framework. | Legislative and regulatory framework
10.3 | 10.3.1, 10.3.2 | Use of international standards | 22 February 2022 | 31 December 2024 | Yes | Yes | WCO | Support to develop policy or procedure on the examination of relevant international standards and to enable Tonga to meet the recommendation of WCO to become RKC compliant. | Legislative and regulatory framework
10.4 | 10.4.1, 10.4.2, 10.4.3, 10.4.4 | Single window | 22 February 2022 | 31 December 2029 | Yes | Yes | Australia, New Zealand | Support to for a feasibility study to investigate viability of a Single Window system and based on results further support to implement - if viable. | Diagnostic and Needs Assessment