## Worksheet
Measure | Items | Measure name | Indicative Implementation Date | Definitive Implementation Date | TA needs notified | Progress reported | Donor / Agency | TA Description | Tags
1.2 | 1.2 | Information available through internet | 31 December 2019 | 30 June 2020 | No | No |  | Stakeholder awareness campaigns to promote the E-Portal | Awareness-raising
1.3 | 1.3 | Enquiry points | 31 December 2020 | 31 December 2020 | No | No |  | • Expand enquiry points beyond ZRA to other Agencies • Strengthen SPS Committee • Establish a national call centre to answer to TF issues • Public awareness campaigns to publicise the national call centre | Information and communication technologies (ICT), Human resources and training, Awareness-raising
1.4 | 1.4 | Notification | 31 December 2022 | 31 December 2025 | No | No |  | Administrative Support for the NCTF Secretariat | Human resources and training
5.1 | 5.1 | Notifications for enhanced controls or inspections | 31 December 2024 | 31 December 2024 | No | No |  | Support for setting up Destination Inspection Yards to encourage further joint inspections by agencies. This support is expected to reduce agencies at the border. | Human resources and training
5.3 | 5.3 | Test procedures | 31 December 2024 | 31 December 2024 | No | No |  | • Infrastructure development of laboratory facilities/onsite laboratory facilities • Implementation of electronic interfaces between the accredited laboratories, XRF Analysers and the ASYCUDA World • Capacity building of staff operating laboratories accreditation of identified laboratories | Information and communication technologies (ICT), Infrastructure and equipment, Human resources and training
6.1 | 6.1 | General disciplines on fees and charges | 31 December 2021 | 31 December 2025 | No | No |  | • Harmonization of statutory fees • Extend the use of the single payment point to all relevant agencies • Stakeholder engagements | Information and communication technologies (ICT), Awareness-raising
6.3 | 6.3 | Penalty Disciplines | 31 December 2019 | 31 December 2024 | No | No |  | • Legislative review • Stakeholder engagement | Legislative and regulatory framework, Awareness-raising
7.1 | 7.1 | Pre-arrival processing | 31 December 2022 | 31 December 2024 | No | No |  | • Automation of Entry and Exit Gates • Introduction of mandatory Pre-Clearance • Stakeholder engagement | Infrastructure and equipment, Human resources and training, Awareness-raising
7.2 | 7.2 | Electronic payment | 31 December 2025 | 31 December 2025 | No | No |  | • Connect all other relevant agencies to the electronic payment system • Stakeholder education on e-payment | Information and communication technologies (ICT), Human resources and training, Awareness-raising
7.4 | 7.4 | Risk management | 31 December 2025 | 31 December 2025 | No | No |  | • ICT technical Infrastructure/back up and security preparedness • Develop Multi-Agency Risk Management Framework • Implement Multi-Agency Risk Management Framework on ASYCUDA World Selectivity Platform • Implement the Governance structures for Multi-Agency Risk Management framework • Capacity building on sustainable operations of Multi-Agency Risk Management Framework • Connect scanners to ASYCUDA World | Information and communication technologies (ICT), Legislative and regulatory framework, Infrastructure and equipment, Institutional procedures, Human resources and training
7.5 | 7.5 | Post-clearance audit | 31 December 2025 | 31 December 2025 | No | No |  | • Capacity building in Post Clearance Audit (PCA) in all relevant government agencies • Stakeholder engagement | Human resources and training, Awareness-raising
7.6 | 7.6 | Average release times | 31 December 2020 | 30 June 2023 | No | No |  | • Support for capacity building for agencies to be able to carry our Time Release Studies in future for sustainability of commitments under Article 7.6 | Diagnostic and Needs Assessment, Human resources and training
7.7 | 7.7 | Authorized operators | 31 December 2024 | 31 December 2024 | No | No |  | • Support for the introduction of the multi-agency framework for the Authorized Economic Operator (AEO) concept • Stakeholder education on benefits of being recognised as Authorized Economic Operator by any agency | Human resources and training, Awareness-raising
7.8 | 7.8 | Expedited shipments | 31 December 2021 | 31 December 2025 | No | No |  | Stakeholder awareness | Awareness-raising
8 | 8 | Border Agency Cooperation | 31 January 2023 | 31 December 2023 | No | No |  | • Stakeholder education on border operations • Support for development of the Regulations for the Coordinated Border Management and Trade Facilitation Act | Legislative and regulatory framework, Human resources and training
10.1 | 10.1.1 | Formalities | 31 December 2021 | 31 December 2024 | No | No |  | • Implementation of electronic Certificates of Origin with SADC, COMESA, EU and Others • Extend the platform to other agencies that issue Import/Export Permits, regulatory approvals under Single Window framework • Stakeholder education on formalities and documentation requirements | Information and communication technologies (ICT), Human resources and training
10.3 | 10.3.1, 10.3.2 | Use of international standards | 31 December 2024 | 31 December 2024 | No | No |  | • Support Zambia Bureau of Standards (ZABS) in order to adopt international standards • Support ZCSA on the application and Implementation of international standards and Conformity Assessment procedures • Domestication of international standards • Stakeholder education on domesticated international standards | Legislative and regulatory framework, Human resources and training, Awareness-raising
10.4 | 10.4 | Single window | 31 December 2030 | 31 December 2030 | No | No |  | • Support the implementation of Phase II of Single Window (remaining twenty-six (26) processes) • Publicity of National Electronic Single Window processes and activities | Information and communication technologies (ICT), Human resources and training
10.6 | 10.6 | Use of customs brokers | 31 December 2022 | 31 December 2025 | No | No |  | • Automate Licensing process for Clearing Agents • Develop Self-Assessment System • Accreditation of Clearing Agencies • Capacity building of Clearing Agents • Stakeholder education on implemented activities | Information and communication technologies (ICT), Human resources and training, Awareness-raising
11 | 11.1, 11.2, 11.3 | Transit | 31 December 2025 | 31 December 2025 | No | No |  | • Implementation of electronic exchange of data with other Customs administrations • Implementation of Electronic Cargo Tracking System (ECTS) within Zambia • Implementation of Electronic Cargo Tracking System along corridors • Implementation of Regional Transit Guarantee Scheme • Stakeholder education on transit procedures and controls | Information and communication technologies (ICT), Awareness-raising
11 | 11.7, 11.8, 11.9, 11.10, 11.11, 11.12, 11.13, 11.14, 11.15, 11.16, 11.17 | Transit | 31 December 2030 | 31 December 2030 | No | No |  | • Implementation of electronic exchange of data with other Customs administration • Implementation of Electronic Cargo Tracking System (ECTS) within Zambia • Implementation of ECTS along corridors • Implementation of Regional Transit Guarantee Scheme • Stakeholder education on transit procedures and controls | Information and communication technologies (ICT), Awareness-raising
12 | 12 | Customs cooperation | 31 December 2038 | 31 December 2038 | No | No |  | • Support for the implementation of OSBPs at the following posts: Nakonde/Tunduma (with Tanzania); Kasumbalesa (with DRC) and Chanida (with Mozambique) • Stakeholder education on implemented reforms | Human resources and training, Awareness-raising