## Worksheet
Mesure | Items | Measure name | Date indicative de mise en œuvre | Date définitive de mise en œuvre | TA needs notified | Progress reported | Donor / Agency | TA Description | Tags
1.1 | 1.1.1 (a), 1.1.1 (b), 1.1.1 (c), 1.1.1 (d), 1.1.1 (e), 1.1.1 (f), 1.1.1 (g), 1.1.1 (h), 1.1.1 (i), 1.1.1 (j) | Publication | 31 décembre 2024 | 31 décembre 2027 | Oui | Non |  | Technical and financial assistance: Project (1): Establishment of the information system relating to the Agreement on Trade Facilitation (TFA)  Assign responsibility for information management project to the Minister of Trade (measure 39);  Produce information to be provided and check that it is user friendly and readable;  Revise legal framework to ensure legal validity and authenticity of information provided;  Define and organize provision of information (different aspects of publication media and outlets, information technology, maintenance, storage and publication of information);  Adopt organizational framework to supervise maintenance of information and establish institutional responsibilities, together with policies or rules, including security rules;  Recruit additional human resources;  Carry out training and capacity building. | Technologies de l’information et de la communication (TIC), Cadre législatif et réglementaire, Ressources humaines et formation
1.2 | 1.2.1 (a), 1.2.1 (b), 1.2.1 (c), 1.2.2, 1.2.3 | Renseignements disponibles sur Internet | 31 décembre 2024 | 31 décembre 2027 | Oui | Non |  | Technical and financial assistance: Project (1): Establishment of the information system relating to the Agreement on Trade Facilitation (TFA)  Assign to National Trade Facilitation Committee (measure 39) the task of drawing up an inventory of relevant projects that might facilitate implementation of this measure;  Revise legal framework to ensure legal validity and authenticity of information provided;  Define and organize provision of information (different aspects of publication media and outlets, information technology, maintenance, storage and publication of information);  Adopt organizational framework to supervise maintenance of information and establish institutional responsibilities;  Ensure systematic use of information and communication technologies (ICTs);  Carry out training and capacity building;  Provide adequate equipment. | Technologies de l’information et de la communication (TIC), Cadre législatif et réglementaire, Infrastructure et equipment, Ressources humaines et formation
1.3 | 1.3.1, 1.3.2, 1.3.3, 1.3.4 | Points d'information | 31 décembre 2024 | 31 décembre 2027 | Oui | Non |  | Technical and financial assistance: Project (1): Establishment of the information system relating to the Agreement on Trade Facilitation (TFA) Estimated cost of project: 272.79 million CFA francs  Establish mechanism for coordination with other agencies, with required cooperation and provision of information (including changing the legal or regulatory framework);  Hold training for staff who will provide the service;  Establish guidelines covering all stages from receiving enquiry to sending reply;  Develop use of standardized communications;  Establish quality control standards and procedures, including deadline for sending replies;  Ensure systematic use of ICTs;  Provide adequate equipment. | Technologies de l’information et de la communication (TIC), Cadre législatif et réglementaire, Infrastructure et equipment, Procédures institutionnelles, Ressources humaines et formation
1.4 | 1.4 (a), 1.4 (b), 1.4 (c) | Notification | 31 décembre 2024 | 31 décembre 2027 | Oui | Non |  | Establish enquiry points. | Technologies de l’information et de la communication (TIC)
5.3 | 5.3.1, 5.3.2, 5.3.3 | Procédures d'essai | 31 décembre 2023 | 31 décembre 2028 | Oui | Non |  | Technical and financial assistance: Project (5): Establishment of a secure system for the importation and exportation of goods in Gabon  Set up an accredited multi sectoral national laboratory;  Obtain ISO certification for other existing laboratories (livestock, consumption, …);  Provide support for veterinary diagnostic laboratory in establishing quality assurance system for purposes of accreditation;  Help with collection of samples needed for tests;  Provide laboratory with aid fund to cover cost of taking samples from livestock;  Change legal or regulatory framework;  Ensure systematic use of ICTs;  Recruit additional human resources;  Carry out training and capacity building for specialist staff (training of employees in specialist schools for biology, chemistry, physics, etc.);  Provide adequate equipment;  Conduct audits of import procedures and processes, particularly inspection of food products, with the assistance of tools or recommendations of relevant international organizations for upgrading the regulatory framework and procedures;  Establish a strategic and operational framework for border agency collaboration;  Computerize formalities relating to sanitary and phytosanitary control procedures and food controls. | Technologies de l’information et de la communication (TIC), Cadre législatif et réglementaire, Infrastructure et equipment, Diagnostic et evaluation des besoins, Procédures institutionnelles, Ressources humaines et formation
7.6 | 7.6.1, 7.6.2 | Temps moyens nécessaires à la mainlevée | 31 décembre 2021 | 31 décembre 2023 | Oui | Non |  | Technical and financial assistance: Project (8): Implementation of a study to determine average release times Estimated cost of project: 110.145 million CFA francs  Carry out study on release of goods (WCO study);  Awareness-raising for other persons working at borders (shipping agents, stevedores, carriers, clearing agents, …);  Establish a focus group involving the customs authority and the different actors involved in the platform (in particular within the National Trade Facilitation Committee (measure 39)). | Diagnostic et evaluation des besoins, Procédures institutionnelles, Sensibilisation
8 | 8.1, 8.2 (a), 8.2 (b), 8.2 (c), 8.2 (d), 8.2 (e) | Coopération entre les organismes présents aux frontières | 31 décembre 2024 | 31 décembre 2031 | Oui | Non |  |  Set up an inter-agency committee for relevant border administrations;  Map procedures, mandates and functioning of all existing entities;  Establish system for monitoring traffic and time periods to measure impact of change with real-time identification of possible bottlenecks at border posts;  Modernize legal framework for border agency cooperation;  Define governance model for adjacent border control posts, including financing modalities for construction, maintenance and operation of facilities. | Technologies de l’information et de la communication (TIC), Cadre législatif et réglementaire, Procédures institutionnelles
10.4 | 10.4.1, 10.4.2, 10.4.3, 10.4.4 | Guichet unique | 31 décembre 2026 | 31 décembre 2035 | Oui | Non |  | Technical and financial assistance: Project (10): Study concerning the establishment of a Single Window for foreign trade Cost of project: 175.245 million CFA francs  Analyse the trade process;  Take the decision to share data between agencies and departments;  Raise awareness of all stakeholders regarding the project (see WCO compendium on the Single Window);  Reinforce ICTs and establish a computerized network system;  Modify the legal or regulatory framework;  Change the institutional and/or administrative structure;  Study the establishment of the Single Window;  Standardize import and export procedures;  Harmonize procedures with other border agencies;  Carry out training and capacity building;  Provide adequate equipment. | Technologies de l’information et de la communication (TIC), Cadre législatif et réglementaire, Infrastructure et equipment, Diagnostic et evaluation des besoins, Procédures institutionnelles, Ressources humaines et formation, Sensibilisation