## Worksheet
Measure | Items | Measure name | Indicative Implementation Date | Definitive Implementation Date | Technical Assistance needs notified | Progress reported | Donor / Agency | TA Description | Tags
1.1 | 1.1.1 | Publication | 31 December 2021 | 31 December 2024 | No | Yes |  |  Training and use of international best practices in relation to publication.  Infrastructure Development for the relevant Agencies.  Training of the relevant agencies' staffs. | Information and communication technologies (ICT), Infrastructure and equipment, Human resources and training
1.2 | 1.2 | Information available through internet | 31 December 2021 | 30 June 2027 | No | Yes |  |  Creation of a comprehensive trade information portal with advanced Information and Communication Technology (ICT) infrastructure.  Website development and Setting criteria and procedures for monitoring & updating the data.  Training of the relevant agencies' staffs.  Technical & Financial support for Translation into one of the official languages of the WTO. | Information and communication technologies (ICT), Infrastructure and equipment, Human resources and training
1.3 | 1.3 | Enquiry points | 31 December 2021 | 30 June 2027 | No | Yes |  |  Development of the TF Enquiry point and Training of the staff.  Establishment of ICT infrastructure and acquisition of Equipment. | Information and communication technologies (ICT), Infrastructure and equipment, Human resources and training
3 | 3 | Advance rulings | 31 December 2021 | 30 June 2027 | No | Yes | USAID, CLDP |  Recognizing & Training on international best practices in the area of Advance rulings.  Training for Customs officers to provide Advance ruling service.  Development of the Information and Communication Technology (ICT) infrastructure.  Providing a software program for an advance ruling system through internet network, that enables the Traders dealing with the customs Authority to obtain all the requested information. | Information and communication technologies (ICT), Infrastructure and equipment, Human resources and training
5.1 | 5.1 | Notifications for enhanced controls or inspections | 31 December 2021 | 31 January 2025 | No | Yes |  |  Establishment of electronic network that links all the border agencies to facilitate the flow of notifications.  Training of the Staff on risk analysis and dealing with such notifications.  providing ICT infrastructure for relevant agencies. | Information and communication technologies (ICT), Infrastructure and equipment, Institutional procedures, Human resources and training
5.3 | 5.3 | Test procedures | 31 December 2022 | 30 September 2023 | No | No |  |  Establishment of Laboratories to undertake testing at all the customs zones.  Development of the existing laboratories and acquisition of equipment.  Training of the Laboratories staff on the use of international best practices.  Establishment of an electronic networking that links all the laboratories to all the related agencies and to link them with the Customs Authority. | Information and communication technologies (ICT), Infrastructure and equipment, Institutional procedures, Human resources and training
6.1 | 6.1 | General disciplines on fees and charges | 31 December 2021 | 30 June 2027 | No | Yes |  |  Development of the ICT infrastructure for the relevant agencies in order to be able to publish all fees & charges in Connection with Importation and Exportation.  Training of the concerned staff in all related agencies on publication and the use of international best practices. | Information and communication technologies (ICT), Infrastructure and equipment, Human resources and training
7.1 | 7.1 | Pre-arrival processing | 31 December 2021 | 30 September 2023 | No | No |  |  Development of the ICT infrastructure for the border agencies and acquisition of equipment.  Establishment of logistics centres at all the border crossings to provide that service.  Training of the border agencies' staffs on the use of best practices in that area.  providing automated system for common risks for data processing before the arrival of the goods. | Information and communication technologies (ICT), Infrastructure and equipment, Human resources and training
7.2 | 7.2 | Electronic payment | 31 December 2021 | 30 September 2023 | No | No |  |  Establishing of administrations in relation to electronic payment at all relevant agencies & establishing a securing system for these financial transactions.  Training of the staff to provide this service.  Development of the ICT infrastructure for the administrations of the electronic payment. | Information and communication technologies (ICT), Infrastructure and equipment, Human resources and training
7.4 | 7.4 | Risk management | 31 December 2021 | 30 June 2027 | No | Yes | United Kingdom, European Union, World Bank, USDA, IFC, KOICA |  Development of the Administration in relation to risk management at the Customs Authority and all the competent authorities and provide the necessary ICT infrastructure.  Training of the related staff to provide that service in accordance with international best practices. | Information and communication technologies (ICT), Infrastructure and equipment, Human resources and training
7.5 | 7.5 | Post-clearance audit | 31 December 2021 | 31 December 2024 | No | Yes | European Union |  Training of the related staff on the latest systems on Accounting & Auditing in consistent with the updates of the e-commerce and transfer pricing.  Provide the necessary ICT infrastructure. | Information and communication technologies (ICT), Infrastructure and equipment, Human resources and training
7.6 | 7.6 | Average release times | 31 December 2021 | 31 March 2023 | No | Yes | United Kingdom, IFC, World Bank |  Providing the programme for the release time measurement which is adopted by the WCO and Training of the staff.  Providing technical support according to the programmes of the WCO. | Information and communication technologies (ICT), Human resources and training
7.7 | 7.7 | Authorized operators | 31 December 2021 | 30 September 2023 | No | Yes | European Union |  Recognizing and Training on international best practices in relation to Authorized operators to expand the scope of the system and to include the small & Medium enterprises.  Development of the necessary ICT infrastructure for the Authorized operator Administration at the Customs Authority. | Information and communication technologies (ICT), Infrastructure and equipment, Human resources and training
7.8 | 7.8 | Expedited shipments | 31 December 2021 | 30 June 2027 | No | Yes | European Union, USDA |  Training of the related staff at the Customs Authority on the use of international best practices according to the programmes of the WCO.  Development of the ICT infrastructure & the X-ray machines.  Setting criteria/new frameworks to comply with the steady increase in the e-commerce imports through expedited shipments. | Information and communication technologies (ICT), Legislative and regulatory framework, Infrastructure and equipment, Human resources and training
7.9 | 7.9 | Perishable goods | 31 December 2021 | 30 September 2023 | No | Yes | USDA |  Establishment of Laboratories to undertake testing for all Perishable Goods at all the customs zones.  Development of the existing laboratories and acquisition of equipment for the expedited release of those goods.  Training of the Laboratories staff on the use of international best practices.  Establishment of an electronic networking to link the laboratories with all the related agencies and to link them with the Customs Authority. | Information and communication technologies (ICT), Infrastructure and equipment, Institutional procedures, Human resources and training
8 | 8 | Border Agency Cooperation | 31 December 2021 | 31 December 2024 | No | Yes | United Kingdom, UNCTAD |  Provide the necessary funds to establish an electronic networking for all the border agencies.  Provide the necessary funds to establish a unified system of procedures to be applicable on the border ports. | Information and communication technologies (ICT), Institutional procedures
10.1 | 10.1.1 | Formalities | 31 December 2021 | 31 December 2024 | No | Yes |  |  Development of the ICT infrastructure for the relevant agencies. | Information and communication technologies (ICT), Infrastructure and equipment
10.2 | 10.2 | Acceptance of copies | 31 December 2021 | 31 December 2024 | No | Yes |  |  Recognizing & Training on the international best practices in relation to the electronic signature & ratification to be able to use the electronic copies of the documents.  Development of the ICT infrastructure for the relevant agencies to enable the usage of the electronic copies of the documents. | Information and communication technologies (ICT), Infrastructure and equipment, Human resources and training
10.3 | 10.3.1, 10.3.2 | Use of international standards | 31 December 2021 | 31 December 2024 | No | Yes |  |  Training of the related agencies' staffs on the use of international best practices in relation to trade facilitation procedures and exchange of experiences with other countries in that area. | Human resources and training
10.4 | 10.4 | Single window | 31 December 2025 | 31 December 2024 | No | Yes |  |  Establishment of systems for electronic networking for all the border agencies to facilitate the operation of the single window  Providing ICT infrastructure for the relevant agencies and the acquisition of necessary equipment.  Re-engineering of the procedures for the competent authorities and coordinating the relevant Data. | Information and communication technologies (ICT), Infrastructure and equipment, Institutional procedures
11 | 11.4, 11.5, 11.6, 11.7, 11.8, 11.9, 11.10, 11.17 | Transit | 31 December 2022 | 30 June 2027 | No | Yes | European Union |  Provide the necessary funds to establish separate lanes for Transit in the Egyptian ports.  Providing x-ray machines at all customs borders related to Transit.  Establishment of a network to link x-ray machines at the national and international level to establish a mechanism for cooperation between customs at borders to exchange the images of Transit trucks.  Establish a GPS System for the Containers and trucks for securing the Transit system.  Providing Track and Trace devices  Recognizing and Training on international best practices in relation to the operation of the Transit system and the use of the international expertise especially European.,  Establishment of an Administration for the response of enquiries in relation to Transit.  Development of the ICT infrastructure for that Administration and the acquisition of necessary equipment. | Information and communication technologies (ICT), Infrastructure and equipment, Institutional procedures, Human resources and training
12 | 12 | Customs cooperation | 31 December 2021 | 31 December 2024 | No | Yes | European Union |  Development of the ICT infrastructure for the Customs Authority and establishing a system for securing the information and maintain its confidentiality.  Training of the Staff on the mechanism of enforcing the Agreements on Administrative Assistance and exchanging information. | Information and communication technologies (ICT), Infrastructure and equipment, Human resources and training