## Worksheet
Measure | Items | Measure name | Indicative Implementation Date | Definitive Implementation Date | Technical Assistance needs notified | Progress reported | Donor / Agency | TA Description | Tags
5.3 | 5.3 | Test procedures | 22 February 2022 | 31 December 2027 | No | No |  | - Support the accreditation of the National Food Testing Laboratory and the Physiochemical Analysis Laboratory. - Development of a new laboratory for Customs. - Training of laboratory staff. | Legislative and regulatory framework, Infrastructure and equipment, Human resources and training
7.2 | 7.2 | Electronic payment | 22 February 2022 | 31 December 2027 | No | No |  | - Development of relevant procedures to implement electronic payment. - Procurement and installation of appropriate technology and equipment. - Training of customs officers and relevant stakeholders on electronic payments and systems. | Information and communication technologies (ICT), Legislative and regulatory framework, Infrastructure and equipment, Human resources and training
7.7 | 7.7 | Authorized operators | 22 February 2022 | 31 December 2025 | No | No |  | - Design and development of an Authorized Operators program. - Training of customs officers and relevant stakeholders. - Development of a monitoring framework for customs to monitor compliance by operators. | Legislative and regulatory framework, Institutional procedures, Human resources and training
8 | 8 | Border Agency Cooperation | 22 February 2020 | 31 December 2027 | No | No |  | - Review and harmonize the procedures that guide the operations of border agencies. - Training of staff of the various regulatory agencies at the borders. - Development of a framework for border agencies to conduct joint clearance. | Legislative and regulatory framework, Institutional procedures, Human resources and training
10.4 | 10.4 | Single window | 22 February 2022 | 31 December 2027 | No | No |  | - Review of relevant laws for the development of a single window. - Procurement of equipment and infrastructure for border agencies. - Capacity building of relevant border agencies staff. | Information and communication technologies (ICT), Legislative and regulatory framework, Infrastructure and equipment, Human resources and training