## Worksheet
Measure | Items | Measure name | Indicative Implementation Date | Definitive Implementation Date | TA needs notified | Progress reported | Donor / Agency | TA Description | Tags
5.3 | 5.3 | Test procedures | 22 February 2019 | 22 February 2025 | No | Yes |  | Legal/Policy Framework • Drafting of legal or formal policy provisions concerning the right to a second test by customs or other relevant border agencies (MOCI, MOH, Quarantine or Fisheries, etc.) as described in the TFA measure. Human Resources/Training • Capacity building training for customs officers on chemical or other products testing. Infrastructure and Equipment • Appropriate facility and equipment for testing. Consultation and Public Awareness • Border agencies and other stakeholder consultation. | Legislative and regulatory framework, Infrastructure and equipment, Human resources and training, Awareness-raising
7.6 | 7.6 | Average release times | 22 February 2019 | 22 February 2022 | No | Yes | WCO | Policy/Procedure • Develop formal policies and procedures for periodic measurement of average release times, to include the processes of all relevant stakeholders at the port/airport/land border within the scope of the study. Infrastructures • Facilitate the setting up of the software in order to establish the TRS platform. • Technology equipment to enhance the establishment of a TRS platform. • Develop a methodology for determining the average release time of goods based on the WCO methodology. Human Resources/Training • Training of customs staff on the operations of TRS platform. • Provide awareness in the form of workshops for the business community and other stakeholders. | Information and communication technologies (ICT), Legislative and regulatory framework, Infrastructure and equipment, Human resources and training, Awareness-raising
7.7 | 7.7 | Authorized operators | 22 February 2019 | 22 February 2025 | No | Yes |  | Legal Framework • Develop relevant legislations to allow the setup of an Authorized Economic Operator (AEO) program. Policy • Develop an authorized economic operator policy. Procedure • Develop proper procedure and criteria for the assessment of AEO that meet specified criteria in the AEO program and in consideration of the ISO 17712:2013. Human Resource/Training • Capacity building and training for customs officers, other border agencies and quarantine officers on the implementation of the AEO and to ensure full compliance with this measure. • Conduct awareness campaigns | Legislative and regulatory framework, Human resources and training, Awareness-raising
10.4 | 10.4 | Single window | 22 February 2023 | 22 February 2025 | No | Yes | World Bank | Legal • Review/develop relevant laws to Facilitate the development of a comprehensive national single window. • Compliance review • Develop a memorandum of understanding (MOU) with other agencies to enhance cooperation. Policy • Conduct a feasibility study to explore the viability of a national single window system. • Develop a strategy for the implementation of a single window. Procedures • Develop appropriate procedures and processes to Facilitate the implementation of a national single window. Human Resources/Training • Capacity building and training of customs officers and officials of other border agencies in order to smoothly implement a national single window system. • Capacity building for officials of other government agencies and private sector on the implementation of a national single window system. Information and Communication Technology • Review of national ICT policies in order to enhance the implementation of a single window. • Enhance and upgrade technological capacities of border agencies and other government agencies necessary to implement a single window. | Information and communication technologies (ICT), Legislative and regulatory framework, Infrastructure and equipment, Diagnostic and Needs Assessment, Human resources and training
12 | 12 | Customs cooperation | 22 February 2018 | 22 February 2025 | No | Yes |  | Infrastructures • Develop an electronic platform for the exchange or sharing of data information and systems interfacing Human Resources/Training and Awareness • Capacity building for external stakeholders and customs officers. • Public sector education and awareness Policy • Formulate policy to improve customs control and for requesting information. • Formulate a compliance instrument to include related policies and action plans. | Information and communication technologies (ICT), Legislative and regulatory framework, Infrastructure and equipment, Human resources and training, Awareness-raising