## Worksheet
Measure | Items | Measure name | Indicative Implementation Date | Definitive Implementation Date | Technical Assistance needs notified | Progress reported | Donor / Agency | TA Description | Tags
1.1 | 1.1.1 | Publication | 1 July 2019 | 31 December 2021 | No | No |  | -Assist in streamlining all information that needs publication from all agencies. -Review of their status of compliance and provide financial support for required additional publication. | Information and communication technologies (ICT), Legislative and regulatory framework
1.2 | 1.2 | Information available through internet | 1 July 2019 | 31 December 2021 | No | No |  | -Support for mapping all agencies procedures and requirements, where relevant support in developing each agency's 'step-by-step' description of the procedures. -Support coordination by the National Trade Facilitation Committee to review each relevant agency's actual status for information through internet and what technical assistance and/or financial assistance is necessary for individual agencies to build information systems. | Information and communication technologies (ICT), Diagnostic and Needs Assessment, Institutional procedures
3 | 3 | Advance rulings | 1 July 2019 | 31 December 2024 | No | No |  | -Capacity building, technical assistance to develop the administrative procedures. | Institutional procedures
7.1 | 7.1 | Pre-arrival processing | 1 July 2021 | 31 December 2021 | No | No |  | -Assistance for capacity building and technical assistance to other authorities than Customs for prearrival processing. | Institutional procedures
7.4 | 7.4 | Risk management | 1 July 2020 | 31 December 2021 | No | No |  | -Support for capacity building, sharing good practices. - Support in reviewing the national legislation and procedures among agencies involved in border control to streamline procedures. -Assistance in establishing criteria for risk assessment and coaching of customs and border agencies officers for implementation of the risk assessment criteria. - Financial assistance for advanced equipment and software for risk management. -Support to improve facilities at border crossings. - Assistance in establishing the integrated risk management | Information and communication technologies (ICT), Legislative and regulatory framework, Infrastructure and equipment, Institutional procedures, Human resources and training
7.5 | 7.5 | Post-clearance audit | 1 July 2020 | 30 June 2024 | No | No |  | -Diagnostic analysis for current PCA situation. - Capacity building in PCA transfer pricing. - Support in the review of and formulation of a legislative framework for transfer pricing. - Training for auditors, training the trainers. | Legislative and regulatory framework, Diagnostic and Needs Assessment, Human resources and training
7.6 | 7.6 | Average release times | 1 July 2020 | 31 December 2021 | No | No |  | - Technical assistance for publication and integration of integrated time release practices. | Information and communication technologies (ICT)
7.7 | 7.7 | Authorized operators | 1 July 2020 | 31 December 2021 | No | No |  | - Technical assistance to implement the revised provisions of the Customs. - Support for good practice exchange and to work with regional and others WTO Members. | Legislative and regulatory framework, Human resources and training
7.8 | 7.8 | Expedited shipments | 1 July 2020 | 31 December 2022 | No | No |  | - Support in reviewing the legislation for urgent consignments and to extend it to other selected goods. - Support for capacity building/coaching of border agencies officers. | Legislative and regulatory framework, Institutional procedures, Human resources and training
7.9 | 7.9 | Perishable goods | 1 July 2020 | 31 December 2021 | No | No |  | - Support GASI prescribes facilities of the operator. - Support to build border crossing facilities for perishable goods. - Assistance for both import and export facilities for animals as well as training for implementation of international best practices and prioritization of border crossings. | Legislative and regulatory framework, Infrastructure and equipment, Human resources and training
8 | 8 | Border Agency Cooperation | 1 July 2019 | 30 June 2025 | No | No |  | - Support in amending the legislation to incorporate a specific provision on national and international border agency cooperation (new law was revoked). - Support and preparation for the organized quarterly meetings with China and Russia. - Support for regular integrated meetings with neighbouring countries (develop joint integrated coordination mechanism between national border agencies (customs, GASI, veterinary and immigration)). - Support in establishing exchange of data. | Information and communication technologies (ICT), Legislative and regulatory framework, Institutional procedures
10.3 | 10.3.1, 10.3.2 | Use of international standards | 1 July 2020 | 31 January 2025 | No | No |  | -Assistance to revise the implementation of standards e.g. GASI on SPS. - Support for capacity building in application of international standards. | Legislative and regulatory framework, Human resources and training
10.4 | 10.4 | Single window | 1 July 2022 | 30 June 2027 | No | No |  | - Assistance to undertake a business process analysis. - Streamline each agency regulations/procedures. - Support for the feasibility study and Single Window blue print. - Support for implementation of the Single Window, including in developing each agency's system. - Support in connecting remoted border crossing points through fibre. | Information and communication technologies (ICT), Infrastructure and equipment, Diagnostic and Needs Assessment, Institutional procedures
10.6 | 10.6 | Use of customs brokers | 1 July 2019 | 31 December 2020 | No | No |  | - Support for capacity building of Customs Brokers in fulfilling their mandate. | Human resources and training